## Лист1
AGREED: | [11 empty] | APPROVING
Director of the Occupational Safety | [11 empty] | Chairman of the Management Board (CEO)
Environmental Inspectorate of JSC NC KTZ | [11 empty] | Vagonservice JSC
EDS Nazyrov S.N. | [11 empty] | EDS _______ Amanbaev G.S.
"_____"______________2024г. | [11 empty] | "_____"________________2024г.
Action plan for environmental activities of Vagonservice JSC for 2025
for environmental activities of Vagonservice JSC for 2025
№ n/a | Name of the event | Place of implementation | Unit of measurement | All you need to do is | The plan for 2025 | Срок выполнения |  |  |  | Responsible executor | Source of funding |  | Economic effect | Note
[6 empty] | 1st quarter | 2nd quarter | 3rd quarter | 4th quarter
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 14 | 15
Section 3. Protection of land resources
3.1. | Demercurization of mercury-containing lamps | LVCHDR-5 Aktobe | tonne | 0.0186 | 0.0186 |  | 0.0093 |  | 0.0093 | LVCHDRG LVCHDRTECH | Operational budget |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated January 2, 2021 No. 400-VI SAM. Section 19. Wastes. Chapter 23 General waste regulations Article 325 Waste disposal
|  | LVHR-1 Uralsk |  | 0.0022 | 0.0022 |  | 0.0011 |  | 0.0011
|  | LVCHDR-2 Atyrau |  | 0.0056 | 0.0056 |  | 0.0028 |  | 0.0028
|  | LVHR-3 Mangyshlak |  | 0.011 | 0.011 |  | 0.0055 |  | 0.0055
|  | LVCHDRU-31 Kyzylorda |  | 0.0166 | 0.0166 |  | 0.0083 |  | 0.0083
|  | LVCHDR-9 Astana |  | 0.0732 | 0.073 |  | 0.0366 |  | 0.0366
|  | LVCHDR-26 Almaty |  | 0.002 | 0.002 |  |  | 0.001 | 0.001
Total: |  |  |  | 0.1292 | 0.129 |  | 0.0636 | 0.001 | 0.0646
3.2. | Disposal of used oils | LVCHDR-5 Aktobe | tonne | 0.13 | 0.13 |  |  | 0.13 |  | LVCHDRG LVCHDRTECH | Operational budget |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated January 2, 2021 No. 400-VI SAM. Section 19. Wastes. Chapter 23 General waste regulations Article 325 Waste disposal
|  | LVHR-1 Uralsk |  | 0.02 | 0.02 |  |  | 0.02
|  | LVCHDR-2 Atyrau |  | 0.07 | 0.07 |  |  | 0.07
|  | LVHR-3 Mangyshlak |  | 0.05 | 0.05 |  |  | 0.05
|  | LVCHDRU-31 Kyzylorda |  | 0.11 | 0.11 |  |  | 0.11
|  | LVCHDR-26 Almaty |  | 0.02 | 0.02 |  |  | 0.01 | 0.01
Total: |  |  |  | 0.4 | 0.4 |  |  | 0.39 | 0.01
3.3. | Disposal of oiled rags | LVCHDR-5 Aktobe | tonne | 0.05 | 0.05 |  | 0.025 |  | 0.025 | LVCHDRG LVCHDRTECH | Operational budget |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated January 2, 2021 No. 400-VI SAM. Section 19. Wastes. Chapter 23 General waste regulations Article 325 Waste disposal
|  | LVHR-1 Uralsk |  | 0.02 | 0.02 |  | 0.01 |  | 0.01
|  | LVCHDR-2 Atyrau |  | 0.04 | 0.04 |  | 0.02 |  | 0.02
|  | LVHR-3 Mangyshlak |  | 0.04 | 0.04 |  | 0.02 |  | 0.02
|  | LVCHDRU-31 Kyzylorda |  | 0.05 | 0.05 |  | 0.025 |  | 0.025
|  | LVCHDR-26 Almaty |  | 0.034 | 0.034 |  |  | 0.017 | 0.017
|  | LVCHDRU-21 Kostanay |  | 0.02 | 0.02 |  | 0.01 |  | 0.01
Total: |  |  |  | 0.254 | 0.254 |  | 0.11 | 0.0165 | 0.127
3.4. | Disposal of used filters | LVCHDR-5 Aktobe | pieces | 6 | 6 |  | 3 |  | 3 | LVCHDRG LVCHDRTECH | Operational budget |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated January 2, 2021 No. 400-VI SAM. Section 19. Wastes. Chapter 23 General waste regulations Article 325 Waste disposal
|  | LVCHDR-2 Atyrau |  | 3 | 3 |  | 2 |  | 1
|  | LVHR-3 Mangyshlak |  | 3 | 3 |  | 2 |  | 1
|  | LVCHDRU-31 Kyzylorda |  | 12 | 12 |  | 6 |  | 6
|  | LVCHDR-26 Almaty |  | 34 | 34 |  |  | 17 | 17
Total: |  |  |  | 58 | 58 |  | 13 | 17 | 28
3.5. | Disposal of contaminated soil | LVCHDR-26 Almaty | tonne | 0.034 | 0.034 |  |  | 0.017 | 0.017 | LVCHDRG LVCHDRTECH | Operational budget |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated January 2, 2021 No. 400-VI SAM. Section 19. Wastes. Chapter 23 General waste regulations Article 325 Waste disposal
|  | LVCHDR-5 Aktobe |  | 15 | 15 |  |  | 15
Total: |  |  |  | 15.034 | 15.034 |  |  | 15.017 | 0.0165
3.6. | Removal of liquid household waste | LVCHDR-5 Aktobe | тонна | 6 | 6 |  |  |  | 6 | LVCHDRG LVCHDRTECH | Operational budget |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated January 2, 2021 No. 400-VI SAM. Section 19. Wastes. Chapter 23 General waste regulations Article 325 Waste disposal
Total: |  |  |  | 6 | 6 |  |  |  | 6
3.7. | Special treatment of contaminated soil after pumping out feces | LVCHDR-5 Aktobe | m3 | 50000 | 50000 | 12500 | 12500 | 12500 | 12500 | LVCHDRG LVCHDRTECH |  |  |  | Compliance with the requirements of the Guidelines for the Environmental Management System of JSC NC KTZ, taking into account the inclusion of obligations of JSC NC KTZ to prevent soil pollution
|  | LVHR-1 Uralsk |  | 33760 | 33760 | 8440 | 8440 | 8440 | 8440
|  | LVCHDR-2 Atyrau |  | 25600 | 25600 | 6400 | 6400 | 6400 | 6400
|  | LVHR-3 Mangyshlak |  | 40000 | 40000 | 10000 | 10000 | 10000 | 10000
|  | LVCHDRU-31 Kyzylorda |  | 102000 | 102000 | 25500 | 25500 | 25500 | 25500
|  | Temir station |  | 30000 | 30000 | 7500 | 7500 | 7500 | 7500
|  | LVCHDR-9 Astana |  | 47371 | 47371 | 11842.75 | 11842.75 | 11842.75 | 11842.75
|  | LVCHDRU-12 Karaganda |  | 2270 | 2270 | 567.5 | 567.5 | 567.5 | 567.5
|  | LVCHDRU-18 Pavlodar |  | 11065 | 11065 | 2766.25 | 2766.25 | 2766.25 | 2766.25
|  | Almaty station |  | 149370 | 149370 | 37342.5 | 37342.5 | 37342.5 | 37342.5
|  | Semey station |  | 11142 | 11142 | 2785.5 | 2785.5 | 2785.5 | 2785.5
|  | Zashita station |  | 7652 | 7652 | 1913 | 1913 | 1913 | 1913
Total: |  |  |  | 510230 | 510230 | 127557.5 | 127557.5 | 127557.5 | 127557.5
3.8. | Disposal of welding electrodes | ЛВЧДР-5 Актобе | tonne | 0.08 | 0.08 |  |  | 0.08 |  | LVCHDRG LVCHDRTECH | Operational budget |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated January 2, 2021 No. 400-VI SAM. Section 19. Wastes. Chapter 23 General waste regulations Article 325 Waste disposal
|  | LVHR-1 Uralsk |  | 0.02 | 0.02 |  |  | 0.02
|  | LVCHDR-2 Atyrau |  | 0.03 | 0.03 |  |  | 0.03
|  | LVHR-3 Mangyshlak |  | 0.02 | 0.02 |  |  | 0.02
|  | LVCHDRU-31 Kyzylorda |  | 0.04 | 0.04 |  |  | 0.04
|  | LVCHDR-26 Almaty |  | 0.0012 | 0.0012 |  |  | 0.006 | 0.006
Total: |  |  |  | 0.1912 | 0.1912 |  |  | 0.196 | 0.006
3.9. | Removal and delivery of industrial waste (MSW) | LVCHDR-5 Aktobe | m³ / tonne | 125 / 27,5 | 125 / 27,5 | 31,25 / 6,875 | 31,25 / 6,875 | 31,25 / 6,875 | 31,25 / 6,875 | LVCHDRG LVCHDRTECH | Operational budget |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated January 2, 2021 No. 400-VI SAM. Section 19. Wastes. Chapter 23 General waste regulations Article 325 Waste disposal
|  | LVHR-1 Uralsk |  | 75 / 16,5 | 75 / 16,5 | 18,75 / 4,125 | 18,75 / 4,125 | 18,75 / 4,125 | 18,75 / 4,125
|  | LVCHDR-2 Atyrau |  | 65 / 14,3 | 65 / 14,3 | 16,25 / 3,575 | 16,25 / 3,575 | 16,25 / 3,575 | 16,25 / 3,575
|  | LVHR-3 Mangyshlak |  | 95 / 20,8 | 95 / 20,8 | 23,75/ 5,2 | 23,75/ 5,2 | 23,75/ 5,2 | 23,75/ 5,2
|  | LVCHDRU-31 Kyzylorda |  | 115 / 25,3 | 115 / 25,3 | 28,75 / 6,325 | 28,75 / 6,325 | 28,75 / 6,325 | 28,75 / 6,325
|  | st. Kazaly |  | 15 / 3,3 | 15 / 3,3 | 3,75 / 0,825 | 3,75 / 0,825 | 3,75 / 0,825 | 3,75 / 0,825
|  | LVCHDR-9 Astana |  | 363,72 / 80,00 | 363,75 / 80,00 | 90,93 / 20,00 | 90,93 / 20,00 | 90,93 / 20,00 | 90,93 / 20,00
|  | LVCHDRU-12 Karaganda |  | 110 / 24,2 | 110 / 24,2 | 27,5 / 6,05 | 27,5 / 6,05 | 27,5 / 6,05 | 27,5 / 6,05
|  | LVCHDRU-18 Pavlodar |  | 110 / 24,2 | 110 / 24,2 | 27,5 / 6,05 | 27,5 / 6,05 | 27,5 / 6,05 | 27,5 / 6,05
|  | LVCHDRU-21 Kostanay |  | 45 / 9,9 | 45 / 9,88 | 11,25 / 2,47 | 11,25 / 2,47 | 11,25 / 2,47 | 11,25 / 2,47
|  | LVCHDR-26 Almaty |  | 1635/245,24 | 1635/245,24 | 408,75/61,31 | 408,75/61,31 | 408,75/61,31 | 408,75/61,31
|  | Accenger station |  | 50/7,5 | 50/7,52 | 12,5/1,88 | 12,5/1,88 | 12,5/1,88 | 12,5/1,88
|  | Zashita station |  | 50/7,5 | 50/7,52 | 12,5/1,88 | 12,5/1,88 | 12,5/1,88 | 12,5/1,88
|  | st.Chu |  | 50/7,5 | 50/7,52 | 12,5/1,88 | 12,5/1,88 | 12,5/1,88 | 12,5/1,88
|  | Aktogay station |  | 50/7,5 | 50/7,52 | 12,5/1,88 | 12,5/1,88 | 12,5/1,88 | 12,5/1,88
Total: |  |  |  | 2953,72 /521,24 | 2953,75/521,30 | 738,43 / 130,325 | 738,43 / 130,325 | 738,43 / 130,325 | 738,43 / 130,325
3.10. | Separate waste collection (waste paper) | LVCHDR-5 Aktobe | kg | 210 | 210 |  |  |  | 210 |  |  |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated December 2, 2021 No. 482
|  | LVCHDR-9 Astana |  | 300 | 300 |  |  |  | 300
|  | LVCHDR-26 Almaty |  | 200 | 200 |  |  |  | 200
Total: |  |  |  | 710 | 710 |  |  |  | 710
3.11. | Separate waste collection (Plastic) | LVCHDR-5 Aktobe | kg | 15 | 15 |  |  |  | 15 |  |  |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated December 2, 2021 No. 482
|  | LVCHDR-9 Astana |  | 13 | 13 |  |  | 13
|  | LVCHDR-26 Almaty |  | 60 | 60 |  |  |  | 60
Total: |  |  |  | 88 | 88 |  |  | 13 | 75
3.12. | Separate waste collection (Glass) | LVCHDR-5 Aktobe |  | 10 | 10 |  |  |  | 10 |  |  |  |  | Compliance with the requirements of the Environmental Code of the Republic of Kazakhstan dated December 2, 2021 No. 482
|  | LVCHDR-9 Astana |  | 13 | 13 |  |  | 13
|  | LVCHDR-26 Almaty |  | 100 | 100 |  |  |  | 100
Total: |  |  |  | 123 | 123 |  |  | 13 | 110
Total for section 3
Total according to the Plan for 2025
Executive Director for Repair and Technical Policy of Vagonservice JSC
Vagonservice JSC | [12 empty] | Н. Смагулов
исп. ЦЛВСПБ- Садуакасова А.А.
тел.: 600-472